## Sheet1
Project Name | Project Manager | Start Date | End Date
Building a CI/CD Pipeline | Miroslav Petkovic | 2021-03-10 | 2021-04-05
Quarter | Month | Week | Task | Difficulty | Responsible | Status | % Complete | Comments
Project Introduction
Q1 | March | 2021-03-10 | Create a Project Plan | Low | Miroslav P. | Complete
|  | 2021-03-11 | Excel Spreadsheet | Low | Miroslav P. | Complete
|  | 2021-03-12 | Trello Board | Low | Miroslav P. | Complete
Design Strucutre
| March | 2021-03-13 | Create Project Scaffolding | Intermediate | Miroslav P. | Complete
|  | 2021-03-15 | Set up Development Structure | Intermediate | Miroslav P. | Complete
|  | 2021-03-17 | Test Code in Azure Cloud Shell | Intermediate | Miroslav P. | Complete
|  | 2021-03-22 | Continuous Integration Setup Github Actions) | High | Miroslav P. | Complete
Continuous Delivery
| March | 2021-03-22 | Set up Azure Pipeline | Low | Miroslav P. | Complete
|  | 2021-03-23 | Create an AppService | Low | Miroslav P. | Complete
|  | 2021-03-27 | Enable Github + Azure Pipelines | Intermediate | Miroslav P. | Complete
|  | 2021-03-30 | Deploy App & Verify Prediction | High | Miroslav P. | Complete
Demo & Submission
| April | 2021-04-01 | Update documentation and create a demo video | High | Miroslav P. | In Process
|  | 2021-04-03 | Project Submssion | Low | Miroslav P. | Not Started
|  | Goals |  |  | Goals
|  | Ensure that the Project is submittted by April 5th |  |  | Al tasks should be marked 'completed' once done